## timeline-data
Date | Document_Title | Document_URL | Case_Num | Markers | Procedural_Step | Environmental_Analysis | Notes
1966-06-28 | 1355 mill st plan | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/1966_06_28_1355%20mill%20st%20plan.PDF | Historical |  | Establishes plotlines | Historical property plan from 1966
1969-02-05 | Full_D0Z6 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/1969_02_05_Full_D0Z6.pdf | Historical |  | Establishes plotlines | Historical property document
2000-07-27 | Quitclaim Deed Lot 2B | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2000_07_27%20Quitclaim%20Deed%20Lot%202B.pdf | Historical |  | Delapa Transfers property to Vinci who pays $10k | Property transfer via quitclaim deed for Lot 2B; ?
2001-04-23 | 338-0303 Review Lot 2B Mill St | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2001_04_23%20338-0303%20Review%20Lot%202B%20Mill%20St.pdf | 338-0303 |  | Substantive, regulation savvy review. This level of scrutiny should be referenced and applied today. | DEP Review under file #338-0303
2014-08-07 | BVW Delineation Field Data Form | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2014_08_07%20BVW%20Delineation%20Field%20Data%20Form.pdf | 338-0594 | 🟢 |  | Prepared by Goddard
2014-08-26 | Wetland Border Report | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2014_08_26%20Wetland%20Border%20Report.pdf | 338-0594 | 🟢 |  | Prepared by Goddard
2014-10-01 | GLM Boundary Delineation | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2014_10%20GLM%20Boundary%20Delineation.png | 338-0594 |  | This changes to BVW in later plans | GLM drafted original.Revised in GEC report; does it reflect GLM's initial image?
2014-10-27 | MISSING: Wetland Delineation Plan RDA | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2014_10_27_MISSING_Wetland_Delineation_Plan_RDA.txt | 338-0594 | ❌⭐ | **RDA** | Initial delineation for development; Critical baseline documentation missing | Filed by GLM Engineering of Hopkinton
2014-11-08 | ANRAD filing | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2014_11_08%20ANRAD%20filing.pdf | 338-0594 | 🟢⭐ | **ANRAD**
2014-11-10 | Affadavit of Service - Nicole Hayes | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2014_11_10%20Affadavit%20of%20Service%20-%20Nicole%20Hayes.pdf | 338-0594 | 🟢 | Abutters Served
2015-09-04 | MISSING: First Gec Site Visit | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_09_04_MISSING_First_GEC_Site_Visit.txt | 338-0594 | ❌ |  | Town hires consultant to verify delineation; WCC not trusting developer's submission | First GEC site visit for peer review
2015-10-07 | MISSING: Second Gec Site Visit | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_10_07_MISSING_Second_GEC_Site_Visit.txt | 338-0594 | ❌ |  | Additional peer review inspection; Thorough review suggests problems found | Second GEC site visit
2015-10-21 | MISSING: Wcc Hearing Gec Peer Review Presentation | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_10_21_MISSING_WCC_Hearing_GEC_Peer_Review_Presentation.txt | 338-0594 | ❌ |  | Peer review contradicts developer's claims; Major problems identified with application | GEC presents findings: dam 60 years old, Mill Brook is perennial, potential vernal pools
2015-10-28 | Conservation Commission minutes 20151028 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_10_28%20Conservation%20Commission%20minutes%2015151028.pdf | 338-0594 | 🟢⛔ | **WCC ANRAD denied** | Developer retreats to state-only jurisdiction; **BOUNDARIES DENIED UNANIMOUS** | *"Motion...that the Request for Wetland Boundary Confirmation for the Bordering Vegetated Wetland, potential Vernal Pool and the Perennial Stream is inaccurate"*; *"the stream must be observed during a non-drought or low flow season"* (Donahue); *"the owner has applied 3 times and has been denied each time"* (Foley)
2015-11-09 | ORAD | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_11_09%20ORAD.pdf | 338-0594 | 🟢⛔ | **WCC ORAD inaccurate** | Formal determination against developer; Perennial stream means much larger buffer zones | Finding BVW delineation inaccurate and Mill Brook perennial
2015-11-20 | MISSING: Delapa Orad Appeal | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_11_20_MISSING_Delapa_ORAD_Appeal.txt | 338-0594 | ❌🟢⭐ | **SORAD appeal** | Challenges perennial stream determination; Weak appeal - missing key evidence | To DEP claiming intermittent stream based on 4 photos
2015-12-09 | Consevation Commission minutes | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_12_09%20Consevation%20Commission%20minutes.pdf | 338-0594 | 🟢🏛️ | **Request to move forum from public view** | Attorney Watsky requests dealing with town attorney directly; Escalation to legal counsel | Communication shifted from public to privileged forum
2015-12-16 | MISSING: Massdep Site Visit | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2015_12_16_MISSING_MassDEP_Site_Visit.txt | 338-0594 | ❌ |  | MassDEP conducts site visit; State begins own review of appeal | 2 additional visits dates unknown
2016-01-13 | Conservation Commssion minutes | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_01_13%20Conservation%20Commssion%20minutes%20.pdf | 338-0594 | 🟢🏛️ | **Delapa Suit Filed** | Attorney Watsky states suit has been filed | *"Nicole Hayes...requested the ANRAD only be heard under the Wetland Protection Act"*; *"If the Bylaw is not removed the only recourse is to file through the superior court"*
2016-01-20 | MISSING: Plan Of Land 44 Mill St Hoyt Surveying | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_01_20_MISSING_Plan_of_Land_44_Mill_St_Hoyt_Surveying.txt | 338-0594 | ❌📐 |  | Survey plan for 44 Mill St; Preparing for subdivision attempt | Hoyt Land Surveying
2016-01-27 | GEC Evaluation | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_01_27%20GEC%20Evaluation.pdf | 338-0594 |  |  | GEC confirms dam 60 years old, Mill Brook perennial, potential vernal pools; Technical evaluation supports WCC position
2016-02-02 | MISSING: Anr Plan 44 Mill St Filed | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_02_02_MISSING_ANR_Plan_44_Mill_St_Filed.txt | 338-0594 | ❌🟢⭐ | **ANR** | ANR Plan for 44 Mill St; Attempt to create buildable lot without subdivision | Map 28, Lot 14
2016-02-09 | Planning Board Meeting Minutes Anr Review | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_02_09%20Westwood%20Planning%20Board%20Minutes | 338-0594 |  | Planning Board reviews ANR application; Initial review of subdivision attempt
2016-02-11 | Planning Board letter RE ANR | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_02_11%20Planning%20Board%20letter%20RE%20ANR.pdf | 338-0594 | 🟢 |  | ANR declared incomplete - vital access not demonstrated; Planning Board finds deficiencies
2016-02-11 | MISSING: Further Anr Materials Submitted | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_02_11_MISSING_Further_ANR_Materials_Submitted.txt | 338-0594 | ❌ |  | Applicant submits additional materials same day; Quick response to deficiency notice
2016-02-23 | Planning Board Meeting Minutes Anr Denial | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_02_23%20Westwood%20Planning%20Board%20Minutes | 338-0594 | 🟢⛔ | **ANR denied** | Planning Board determines land constitutes subdivision | Must go through full subdivision process
2016-02-24 | Nora Loughnane Planning Board Letter | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_02_24%20Nora%20Loughnane%20Planning%20Board%20Letter.pdf | 338-0594 |  | Correspondence from Nora Loughnane to Planning Board; Public participation in process
2016-03-19 | 21 DeMelle - Catrone - Dam Ownership | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_03_19-21%20DeMelle%20-%20Catrone%20-%20Dam%20Ownership | 338-0594 |  | Email exchange about dam ownership; First questioning of dam ownership responsibilities
2016-04-29 | Buckley to Abutters | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_04_29%20Buckley%20to%20Abutters | 338-0594 |  | Community communication to abutters
2016-06-13 | MISSING: Revised Plan | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_06_13_MISSING_Revised_Plan.txt | 338-0594 | ❌🟢📐 |  | Delapa submits revised plan in response to previous comments | Continuing permit pursuit
2016-08-25 | SOC_highlighted | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_08_25%20SOC_highlighted.pdf | 338-0594 | 🟢⛔ | **DEP SORAD denied** | DEP confirms Mill Brook as perennial stream; site within Interim Wellhead Protection Area for public water supply | *"A significant portion of Mill Brook including the impoundment at the site is within the Interim Wellhead Protection Area of a Public Water Supply (PWS) well at Buckmaster Pond in Westwood...The IWPA radius for the PWS well at Buckmaster Pond is 0.5 miles."* Protected status emphatically upheld Site described in filing as "undevelopable"
2016-08-30 | Buckley to Abutters | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_08_30%20Buckley%20to%20Abutters | 338-0594 |  | Community communication to abutters
2016-09-15 | MISSING: Dep Appeal Document | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_09_15_MISSING_DEP_Appeal_Document.txt | 338-0594 | 🔒❌🟢⭐ | **SORAD appealed** | Delapa appeals DEP's Superseding Order; Opens second appeal (Docket WET-2016-022) | Escalates to administrative hearing - challenges state's environmental findings
2016-09-19 | 20 Buckley - Catrone - Palmer | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_09_19-20%20Buckley%20-%20Catrone%20-%20Palmer | 338-0594 |  | Community communication between neighbors | Buckley, Catrone, Palmer coordination
2016-10-20 | #338-0594 DEP FORAD | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_10_20%20%23338-0594%20DEP%20FORAD.pdf | 338-0594 | 🔒🟢✅ | **DEP FORAD issued** | DEP confirms resource area boundaries; Legally binding wetland delineation | Developer wins - boundaries denied multiple times by WCC and DEP are approved
2016-11-09 | MISSING: Executive Session Minutes | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_11_09_MISSING_Executive_Session_Minutes.txt | 338-0594 | 🔒❌ |  | WCC executive session for private deliberations on strategy | Settlement discussions begin
2016-11-10 | MISSING: Settlement Agreement Watsky | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_11_10_MISSING_Settlement_Agreement_Watsky.txt | 338-0594 | 🔒❌ |  | Settlement agreement with attorney Watsky; Legal resolution attempt | First settlement effort
2016-11-21 | MISSING: Settlement Agreement Worrall | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_11_21_MISSING_Settlement_Agreement_Worrall.txt | 338-0594 | 🔒❌ |  | Settlement agreement with Worrall; Another party settlement | Multiple settlements needed
2016-12-19 | delapawet2016-022fd_OCR | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_12_19%20delapawet2016-022fd_OCR.pdf | 338-0594 | 🔒🟢✅ | **DEP Proceedings Dismissed** | DEP Final Decision incorporating Settlement Agreement; Appeal proceedings dismissed; BVW and Mill Brook perennial stream/Riverfront confirmed | *"I have reviewed the attached Settlement Agreement...The Department issues this Final Decision incorporating the Settlement Agreement and Final Order of Resource Area Delineation"*; *"these proceedings are dismissed with the parties waiving whatever rights they may have to further administrative review"*
2016-12-19 | MISSING_MassDEP_FORAD_Technical_Document | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_12_19_MISSING_MassDEP_FORAD_Technical_Document.txt | 338-0594 | ❌🔒🟢 |  | FORAD technical delineation document DEP File #338-0594; Actual wetland boundary maps/plans | 3-year term expires Dec 19, 2019; Contains the specific delineated boundaries referenced in settlements
2016-12-19 | MISSING: Dep Final Decision Forad | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_12_19_MISSING_DEP_Final_Decision_FORAD.txt | 338-0594 | ❌ |  | DEP Final Decision issuing FORAD; Final boundaries set with time limit | Expires Dec 19 2022 with extension; Clock starts ticking for development
2016-12-19 | MISSING: Dep Docket Wet-2016 022 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_12_19_MISSING_DEP_Docket_WET-2016_022.txt | 338-0594 | ❌ |  | DEP Docket No. WET-2016_022 official case number | Administrative tracking
2016-12-19 | MISSING: Dep File Sorad 338-0594 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2016_12_19_MISSING_DEP_File_SORAD_338-0594.txt | 338-0594 | ❌ |  | File No. SORAD/338-0594 reference | Key SORAD file for appeals
2017-01-11 | Conservation Commission Minutes | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2017_01_11%20Conservation%20Commission%20Minutes.pdf | 338-0594 | 🔒🟢✅ | **WCC accepts ORAD** | Commission signs ORAD for approval under Westwood Wetland Bylaw (approved 11/9/16 in Executive Session); Official wetland boundaries established under local bylaw with 3-year validity | *"the Commission must sign an ORAD for approval under the Bylaw which was approved on 11/9/16 during Executive Session"*; *"Motion...to sign the ORAD for approval under the Westwood Wetland Bylaw"*
2018-11-02 | Site_Plan | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2018_11_02_Site_Plan.pdf | 338-0594 | 🔒🟢 |  | New site plan developed with updated development proposal | Preparing for next permit attempt
2019-12-17 | FORAD filing | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2019_12_17%20FORAD%20filing.pdf | 338-0594 | 🔒🟢 |  | DEP #338-0594 FORAD formal filing
2019-12-24 | #338-0594 Extension Permit for FORAD | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2019_12_24%20%23338-0594%20Extension%20Permit%20for%20FORAD.pdf | 338-0594 | 🔒🟢♻️ | **FORAD Extension** | WETLAND BOUNDARIES EXTENDED (3 more years until Dec 19, 2022) | Boundaries remain locked despite changing conditions
2020-03-19 | Delapa NOI | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_03_19%20Delapa%20NOI.pdf | 338-0706 | 🟢⭐ | **NOI** | New development application | Starting formal permit process
2020-04-07 | Vinci_Quitclaim_Deed | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_04_07_Vinci_Quitclaim_Deed.pdf | Historical |  | Property transfer via quitclaim deed from Vinci back to Delapa for $1
2020-04-15 | Tim McGuire Abutters List | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_04_15%20Tim%20McGuire%20Abutters%20List.pdf | 338-0706 |  | List of property abutters required for notifications | Procedural requirement
2020-05-11 | Delapa 335-5 NOI Checks | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_05_11%20Delapa%20335-5%20NOI%20Checks.pdf | 338-0706 |  | Filing fee payment checks for NOI | Meeting financial obligations
2020-05-11 | Delapa NOI Wetland Fee Transmittal Form | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_05_11%20Delapa%20NOI%20Wetland%20Fee%20Transmittal%20Form.pdf | 338-0706 |  | Fee transmittal documentation; Administrative paperwork | Procedural compliance
2020-06-18 | Tim McGuire Affadavit of Service to Abutters | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_06_18%20Tim%20McGuire%20Affadavit%20of%20Service%20to%20Abutters.pdf | 338-0706 |  | Proof of abutter notification; Legal requirement met | Avoiding procedural challenges
2020-06-18 | Goddard_NOI_Original_Vinci #338-0706 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_06_18_Goddard_NOI_Original_Vinci%20%23338-0706.pdf | 338-0706 | 🟢📐 |  | WPA Form 3 for single-family home on Vinci property; Formal development application | Engineer representing new owner
2020-07-08 | Minutes Conservation Commission | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_07_08%20Minutes%20%20Conservation%20Commission.pdf | 338-0706 |  | Initial hearing on single-family home NOI; Site has pond, dam, riverfront area, BVW and flood plain | *"Mr. Goddard states this is a four acre lot with a pond, dam, riverfront area, bordering vegetated wetland and flood plain"*; *"Mr. Rogers states there are a lot of significant issues on this site"*; *"Motion...to hire a peer review consultant at the expense of the applicant"*
2020-09-09 | MISSING: Concom Minutes Peer Review Ordered | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_09_09_MISSING_ConCom_Minutes_Peer_Review_Ordered.txt | 338-0706 | 🟢❌ |  | WCC formally orders peer review; Independent evaluation required | Wrong document on town site - July 22 minutes posted instead; Town maintaining scrutiny
2020-10-08 | GEC_Donahoe_Review_Summary | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_10_08_GEC_Donahoe_Review_Summary.pdf | 338-0706 | 🟢🔍 |  | GEC/Donahoe peer review summary; Professional evaluation findings | SCALE ERROR FOUND ON STAMPED PLAN
2020-10-13 | Goddard to Catrone | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_10_13%20Goddard%20to%20Catrone.pdf | 338-0706 |  | Goddard email to WCC administrator; Correcting NOI filing under Vinci instead of Delapa
2020-10-14 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_10_14%20WCC%20Hearing%20Continued.txt | 338-0706 | 🐢 |  | Hearing continuation notice; More time needed for review | Process extending
2020-10-27 | Response_to_Peer_Review_Comments | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_10_27_Response_to_Peer_Review_Comments.pdf | 338-0706 |  | Applicant responds to peer review; Addressing technical concerns | Attempting to satisfy critics
2020-10-28 | Minutes Conservation Commission | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_10_28%20Minutes%20%20Conservation%20Commission.pdf | 338-0706 |  | Conservation Commission meeting acknowledges site history | *"It has been before the Commission several times in the past"* (Previtera); Difficult site with repeated attempts - pattern of persistent applications
2020-11-18 | Plot Sale Record - Salvatore - Delapa | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_11_18%20Plot%20Sale%20Record%20-%20Salvatore%20-%20Delapa.pdf | Historical |  | Property transfer documentation | Sale record from Salvatore to Delapa
2020-11-18 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_11_18%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Another hearing continuation
2020-12-14 | GEC_Donahoe_Review_Comments | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2020_12_14_GEC_Donahoe_Review_Comments.pdf | 338-0706 | 🟢 |  | Detailed peer review reveals specific technical concerns | Substantive issues identified with application
2021-01-01 | 2021 Goddard Continuation Requests | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021%20Goddard%20Continuation%20Requests.pdf | 338-0706 | 🐢 |  | Pattern of delays by applicant | Multiple continuation requests by Goddard
2021-01-04 | Enviro Analysis Follow up Email from Brian Donahoe | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_01_04%20Enviro%20Analysis%20Follow%20up%20Email%20from%20Brian%20Donahoe.pdf | 338-0706 |  | Peer reviewer finalizing environmental analysis | Follow-up email from Brian Donahoe
2021-01-27 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_01_27%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Hearing continuation
2021-02-10 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_02_10%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Another continuation
2021-02-24 | WCC Hearing Contnued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_02_24%20WCC%20Hearing%20Contnued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Continued again
2021-03-10 | Delapa Site Plan | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_03_10%20Delapa%20Site%20Plan.pdf | 338-0706 | 🟢📐 |  | Updated development proposal | Site plan revision submitted
2021-03-10 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_03_10%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Procedural reset required due to extended delays | WCC requires re-notification of abutters due to many continuations
2021-03-19 | Delapa - Goddard Property owner Application Authorizatoin | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_03_19%20Delapa%20-%20Goddard%20Property%20owner%20Application%20Authorizatoin.pdf | 338-0706 |  | Formal agent authorization | Authorization for Goddard to represent Delapa
2021-03-19 | Delapa Notice of Intent Form 3 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_03_19%20Delapa%20Notice%20of%20Intent%20Form%203.pdf | 338-0706 | 🟢 |  | Updated formal application submitted | WPA Form 3 submission
2021-03-19 | Goddard Response to GEC Review | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_03_19%20Goddard%20Response%20to%20GEC%20Review.pdf | 338-0706 | 🟢 |  | Applicant addresses technical concerns raised by peer reviewer | Response to GEC Review comments
2021-03-22 | Goddard_NOI_Revised_DEP_338-0706 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_03_22_Goddard_NOI_Revised_DEP_338-0706.pdf | 338-0706 | 🟢📐 |  | Application revision for case #338-0706 | Revised plans submitted
2021-03-24 | WCC Hearing Continued - Abutters not notified | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_03_24%20WCC%20Hearing%20Continued%20-%20Abutters%20not%20notified.pdf | 338-0706 | 🐢 |  | Procedural failure requires new notification | Abutters not properly notified
2021-04-26 | Catrone email to Donahoe | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_04_26%20Catrone%20email%20to%20Donahoe.pdf | 338-0706 |  | Administrative coordination with peer reviewer | Catrone email to Donahoe
2021-05-05 | Minutes Conservation Commission | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_05_05%20Minutes%20%20Conservation%20Commission.pdf | 338-0706 | 🐢 |  | Commission deliberation documentation | WCC meeting minutes
2021-05-26 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_05_26%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Another hearing continuation
2021-06-09 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_06_09%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Hearing continuation
2021-07-03 | Delapa NOI Form 3 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_07_03%20Delapa%20NOI%20Form%203%20Revision.pdf | 338-0706 | 🟢⭐ | **NOI** | Updated application materials with July 3, 2021 date | WPA Form 3 Revision
2021-07-03 | Delapa Revised Site Plan | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_07_03%20Delapa%20Revised%20Site%20Plan.pdf | 338-0706 | 🟢📐 |  | Updated development proposal | Revised site plan dated July 3, 2021
2021-07-28 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_07_28%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Another continuation
2021-09-08 | Goddard response to GEC Review | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_09_08%20Goddard%20response%20to%20GEC%20Review.jpg | 338-0706 | 🟢 |  | Applicant disputes peer review findings | Goddard rejects GEC peer review
2021-09-08 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_09_08%20WCC%20Hearing%20Continued.pdf | 338-0706 | 🐢 |  | Extended review process continues | Hearing continuation
2021-10-08 | Goddard Revised NOI Site Plan | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_10_08%20Goddard%20Revised%20NOI%20Site%20Plan.pdf | 338-0706 | 🟢📐 |  | Additional design modifications | Another revised site plan
2021-10-13 | Minutes Conservation Commission | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_10_13%20Minutes%20%20Conservation%20Commission.pdf | 338-0706 | 🟢🏛️ |  |  | Mr McGuire states if the project is going to e denied he will ask the commission if they will continue the bylaw section of the Notice of Intent for six (6) months. Ms. Catrone recommends the Commission not break up the state and bylaw portion of the Notice of Intent. Hearing continued to allow Karon to consult with Town Counsel on continuing the bylaw portion of the Notice of Intent.
2021-10-18 | Delapa Withdrawal of NOI from Town Bylaws | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_10_18%20Delapa%20Withdrawal%20of%20NOI%20from%20Town%20Bylaws.pdf | 338-0706 | 🔒🟢 |  | Strategic retreat to state-only jurisdiction before any vote; Attempt to avoid stricter town standards | *"Applicant hereby **withdraws its local-by-law Notice of Intent ⭐**…"* (Complaint p. 8 ¶38)
2021-10-27 | WCC Hearing Continued - Mr Stephen David recuses himself | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_10_27%20WCC%20Hearing%20Continued%20-%20Mr%20Stephen%20David%20recuses%20himself.pdf | 338-0706 | 🐢 |  | Commissioner recusal affects voting composition | Mr Stephen David recuses himself
2021-11-10 | Minutes Conservation Commission | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_11_10%20Minutes%20%20Conservation%20Commission.pdf | 338-0706 | 🟢🏛️ |  | **PROJECT DENIED 7-0** - Board refuses withdrawal & issues denial; Commission protects 26,638 sf of resources including perennial stream | *"Motion...to deny...under both the state and the bylaw. The site is very difficult and the applicant has not demonstrated that the project can meet the performance standards"* (Complaint p. 8 ¶39)
2021-11-17 | Order_of_Conditions_Denial #338-0706 - #438-0706 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_11_17_Order_of_Conditions_Denial%20%23338-0706%20-%20%23438-0706.pdf | 338-0706 | 🟢⛔ | **DEP NOI denied** | Formal agency action creates appealable record; 26,638 sf impact, perennial stream, 10 ft NDZ violations cited | WPA Form 5 denial citing environmental impacts
2021-11-18 | WCC Denial of NoI | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_11_18%20WCC%20Denial%20of%20NoI.pdf | 338-0706 | 🟢⛔ | **WCC NOI denied** | Official rejection of development proposal | Formal WCC denial document
2021-11-30 | Goddard DEP SOC Request | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_11_30%20Goddard%20DEP%20SOC%20Request.jpg | 338-0706 | 🔒🟢⭐ | **SOC appeal** | Seeks state override of local denial; claims project meets standards with 700 sq ft replication for 550 sq ft fill | Appeal to DEP for superseding order
2021-12-15 | DEP Site Inspection Notice | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2021_12_15%20DEP%20Site%20Inspection%20Notice.pdf | 338-0706 |  | DEP schedules site visit for SOC review | Site inspection notice
2022-01-06 | MISSING: Dep Site Visit Notes | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_01_06_MISSING_DEP_Site_Visit_Notes.txt | 338-0706 | ❌ |  | Critical inspection with all parties present; DEP evaluates conflicting positions | Site visit with applicant, WCC rep, and peer reviewer
2022-01-11 | DEP letter to Delapa | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_01_11%20DEP%20letter%20to%20Delapa.pdf | 338-0706 | 🔒🟢 |  | DEP requests quantification of BLSF impacts and flood storage per 310 CMR 10.57(4) | Request for additional technical information
2022-01-12 | Case Details - Massachusetts Trial Court N3 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_01_12_Case%20Details%20-%20Massachusetts%20Trial%20Court%20N3.pdf | 338-0706 | 🔒🟢 |  | Legal challenge escalates to superior court | Superior Court Case – Docket #2282CV00038 opened
2022-01-12 | DelapavsWCC_Docket001_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_01_12_DelapavsWCC_Docket001_OCR2.pdf | 338-0706 | 🔒🟢 |  | Formal legal challenge to WCC denial; 3 counts: certiorari, by-law not stricter, Commission lacked withdrawal discretion | Superior Court Filing – Petition for Certiorari (31 pages)
2022-01-12 | DelapavsWCC_Docket002_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_01_12_DelapavsWCC_Docket002_OCR2.pdf | 338-0706 | 🔒 |  | Procedural filing for court case | Superior Court Filing – Certificate of Service of Petition
2022-02-07 | Legal Negotiation | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_02_07%20Legal%20Negotiation.pdf | 338-0706 | 🔒🟢 |  | Settlement negotiations begin between parties | Legal negotiation documentation
2022-02-08 | Goddard Information Request | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_02_08%20Goddard%20Information%20Request.pdf | 338-0706 | 🔒 |  | Response to DEP with revised plans dated Jan 31, 2022 | Goddard submits information request response
2022-02-23 | MISSING: Dep Cut Fill Request | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_02_23_MISSING_DEP_Cut_Fill_Request.txt | 338-0706 | ❌🔒 |  | DEP follow-up request for cut and fill table data | Follow-up to Jan 11 request
2022-02-25 | MISSING: Blsf Cut Fill Chart | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_02_25_MISSING_BLSF_Cut_Fill_Chart.txt | 338-0706 | ❌🔒 |  | Technical submission responding to DEP request | BLSF cut/fill chart submitted
2022-03-07 | Letter from DEP to Delapa | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_03_07%20Letter%20from%20DEP%20to%20Delapa.pdf | 338-0706 | 🔒🟢 |  | DEP identifies technical issues with application | Inconsistent floodplain elevations noted
2022-03-14 | Delapa Letter | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_03_14%20Delapa%20Letter.pdf | 338-0706 | 🔒 |  | Response to DEP with new revised plans dated March 8, 2022 | Delapa letter submitting plan revisions
2022-03-21 | Email Donahoe - Catrone | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_03_21%20Email%20Donahoe%20-%20Catrone%20.pdf | 338-0706 |  | Communication between peer reviewer and WCC administrator | Email correspondence
2022-03-28 | Brian Donahoe - Karon email | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_03_28%20Brian%20Donahoe%20-%20Karon%20email.pdf | 338-0706 |  | Peer reviewer communication | Brian Donahoe correspondence
2022-03-31 | DelapavsWCC_Docket003_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_03_31_DelapavsWCC_Docket003_OCR2.pdf | 338-0706 | 🔒 |  | Court filing with attorney affidavit | Superior Court Filing – Certificate of Service Documents (Rachel Watsky affidavit)
2022-03-31 | DelapavsWCC_Docket004_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_03_31_DelapavsWCC_Docket004_OCR2.pdf | 338-0706 | 🔒 |  | Procedural court filing | Superior Court Filing – Acceptance of Service
2022-04-01 | Re Request of Suerpseding Order Letter from Town Counsel | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_04_01%20Re%20Request%20of%20Suerpseding%20Order%20Letter%20from%20Town%20Counsel.pdf | 338-0706 | 🔒🟢 |  | Town Counsel challenges SOC request with pointed questions | Letter responding to superseding order request
2022-04-20 | DelapavsWCC_Docket005_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_04_20_DelapavsWCC_Docket005_OCR2.pdf | 338-0706 | 🔒 |  | WCC legal defense strategy | Superior Court Filing – Answer denying claims and asserting affirmative defenses
2022-05-06 | Superseding Order of Conditions | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_05_06_Superseding%20Order%20of%20Conditions.pdf | 338-0706 | 🔒🟢✅ | **SOC issued** | DEP overrules WCC denial; state authority supersedes local decision with conditions | WPA Form 5 with reserved rights for additional issues
2022-05-07 | Note on SOC Covid Extension | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_05_07%20Note%20on%20SOC%20Covid%20Extension | 338-0706 |  | Legal clarification on permit validity | COVID extension does NOT apply to SOC
2022-05-19 | 338-0706 Letter from Town Counsel | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_05_19%20338-0706%20Letter%20from%20Town%20Counsel.pdf | 338-0706 | 🔒🟢 |  | Town Counsel identifies additional regulatory gap | Shared driveway issue - no planning board order
2022-08-14 | DelapavsWCC_Docket006_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_08_14_DelapavsWCC_Docket006_OCR2.pdf | 338-0706 | 🔒 |  | Court manages case progress | Superior Court Order – Status Review (update required by 09/09/2022)
2022-08-23 | Notice - Order of Status Review | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_08_23%20Notice%20-%20Order%20of%20Status%20Review.pdf | 338-0706 | 🔒 |  | Court administrative notice | Notice of Status Review Order
2022-09-08 | DelapavsWCC_Docket007_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_09_08_DelapavsWCC_Docket007_OCR2.pdf | 338-0706 | 🔒🟢 |  | Settlement negotiations progress; parties need time for formal approval | Superior Court Filing – Joint Status Report
2022-09-09 | DelapavsWCC_Docket008_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_09_09_DelapavsWCC_Docket008_OCR2.pdf | 338-0706 | 🔒 |  | Court grants additional time for settlement completion | Superior Court Order – Status review continued to November 9, 2022
2022-09-12 | letter from Goddard | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_09_12%20letter%20from%20Goddard.pdf | 338-0706 | 🔒🟢 |  | Settlement proposal with financial cap | Goddard proposes dam repair with $25,000 cost cap
2022-09-12 | Unsigned Settlement Agreement | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_09_12%20Unsigned%20Settlement%20Agreement.pdf | 338-0706 | 🔒🟢 |  | Draft settlement terms negotiated | WCC accepts SOC, Delapa repairs dam, new NOI required
2022-10-26 | 42 Mill Street signed MOU 10-26-2022 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_10_26_42%20Mill%20Street%20signed%20MOU%2010-26-2022.pdf | 338-0706 | 🔒🟢✅ | **Settlement executed** | Legal dispute resolved; Commission adopts DEP SOC with conditions: Delapa repairs dam first, then building permit | MOU with $25,000 cost cap
2022-12-19 | Referenced in SOC |  | 338-0594 | 🔒🟢⏰ | **FORAD expires** | Critical regulatory protection expires; site returns to undelineated status requiring new wetland delineation | 6-year term ends (3+3 extension)
2022-12-20 | DelapavsWCC_Docket009_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2022_12_20_DelapavsWCC_Docket009_OCR2.pdf | 338-0706 | 🔒 |  | Court docket entry - Joint status update
2023-03-27 | DelapavsWCC_Docket010_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_03_27_DelapavsWCC_Docket010_OCR2.pdf | 338-0706 | 🔒 |  | Court docket entry - Status review order
2023-04-24 | DelapavsWCC_Docket011_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_04_24_DelapavsWCC_Docket011_OCR2.pdf | 338-0706 | 🔒 |  | Status review - case settled, 60-day order issued
2023-04-24 | DelapavsWCC_Docket012_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_04_24_DelapavsWCC_Docket012_OCR2.pdf | 338-0706 | 🔒🟢 |  | Court action contingent on settlement completion | Superior Court Order – Dismissal Nisi
2023-05-22 | Dam_Restoration_Site_Plan_Figure4 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_05_22_Dam_Restoration_Site_Plan_Figure4.pdf | 338-0756 | 🟢 |  | Technical engineering submission for dam project | Dam restoration site plan Figure 4
2023-05-23 | WPA_Form_3_NOI_Dam_Restoration | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_05_23_WPA_Form_3_NOI_Dam_Restoration.pdf | 338-0756 | 🟢⭐ | **NOI** | Dam restoration application per settlement agreement requirements | WPA Form 3 for dam restoration
2023-05-27 | DeMelle - Catrone Dam Ownership | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_05_27%20DeMelle%20-%20Catrone%20Dam%20Ownership | 338-0756 |  | Legal questions about dam ownership responsibility | Community inquiry on dam ownership
2023-06-14 | Legal_Notice_Dam_Restoration_Hearing | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_06_14_Legal_Notice_Dam_Restoration_Hearing.pdf | 338-0756 |  | Public notification for regulatory hearing | Legal notice for dam restoration hearing
2023-06-22 | DelapavsWCC_Docket013_OCR2 | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_06_22_DelapavsWCC_Docket013_OCR2.pdf | 338-0706 | 🔒🟢 |  | Final resolution of legal challenge | Superior Court Filing – Stipulation of Dismissal (with prejudice, parties bear own costs)
2023-06-28 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_06_28%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🐢 |  | Extended review process for dam restoration | Hearing continued
2023-06-29 | FOIA_REQUEST FORMALLY FILED | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_06_29_FOIA_REQUEST%20FORMALLY%20FILED | 338-0756 |  | Public records request for case documentation | DeMelle FOIA request filed
2023-07-12 | Minutes Conservation Commission | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_07_12%20Minutes%20%20Conservation%20Commission.pdf | 338-0756 | 🟢🏛️ |  | Commission discusses dam project logistics and cost constraints | Dam repair discussion: $25k cap, mini excavator access
2023-07-26 | Minutes Conservation Commission | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_07_26%20Minutes%20%20Conservation%20Commission.pdf | 338-0756 | 🟢🏛️ |  | Legal and environmental complications emerge | Dam ownership questioned; beaver removal concerns raised
2023-09-01 | #NAME? | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_09_01%20-%20Response-booklet_Mon_Sep_11_2023_09-01-40.pdf | 338-0756 | 🟢📐 |  | Technical response to peer review analysis | Response to BETA peer review citing SOC #338-0706
2023-09-13 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_09_13%20%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🐢 |  | Extended review process continues | Hearing continued
2023-09-27 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_09_27%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🐢 |  | Extended review process continues | Hearing continued
2023-10-11 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_10_11%20%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🐢 |  | Extended review process continues | Hearing continued
2023-10-25 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_10_25%20%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🐢 |  | Extended review process continues | Hearing continued
2023-11-08 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_11_08%20%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🐢 |  | Extended review process continues | Hearing continued
2023-12-13 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_12_13%20%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🐢 |  | Extended review process continues | Hearing continued
2023-12-31 | MISSING: Beta Final Peer Review Report | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2023_MISSING_BETA_Final_Peer_Review_Report.txt | 338-0756 | ❌🟢 |  | Critical peer review analysis missing | BETA final peer review report for dam project
2024-01-10 | WCC Hearing Continued | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2024_01_10%20%20WCC%20Hearing%20Continued.pdf | 338-0756 | 🟢🏛️ |  | Procedural reset required due to extended delays | Applicant must re-notify abutters
2025-05-06 | Referenced in recent correspondence |  | 338-0706 | 🔒🟢⏰ | **SOC expires** | Critical regulatory protection expires; no valid development approval remains | 3-year term ends for SOC #338-0706
2025-07-23 | WCC Meeting | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2025_07_23_MISSING%20minutes%20conservation%20commission.pdf | 338-0756 | ❌🟢🏛️ |  | Major shift from settlement agreement; Delapa proposes dam removal instead of repair citing cost | Continued to September; significant change from original MOU
2025-07-29 | DeMelle email to Catrone | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/2025_07_29%20DeMelle%20email%20to%20Catrone | 338-0756 |  | Community input on current proceedings | Email to WCC administrator
| USGIS Orthophoto View of Locus Site - Lot 2B Mill St | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/USGIS%20Orthophoto%20View%20of%20Locus%20Site%20-%20Lot%202B%20Mill%20St.pdf | Historical |  | Visual site documentation | USGS orthophoto aerial view of Lot 2B Mill St
| USGS Site Locus - Lot 2B Mill St | https://github.com/tdemelle-SiP/bakers_pond/blob/master/Dated%20Documents/USGS%20Site%20Locus%20-%20Lot%202B%20Mill%20St.pdf | Historical |  | Geographic reference documentation | USGS site location map for Lot 2B Mill St